## ISSUES
SANMAR - VMS - ISSUES REGISTER
# | Description | Reported By | Sanmar Testing | Sanmar testing- 13th Feb | Sanmar testing - 21st Feb | Status | Severity | Type | Reported Date | Resolved Date | Closed date | Resolution | Existing Output | Preferred Output | Developer Comments
1 | iPAD - Rename Desktop icon name to "SANMAR VMS" instead of "Chairman" | Jeba Raj | OK |  |  | New | 4 - Cosmetic | Functional | 2018-01-20 | 2018-01-25 |  | Fixed
2 | iPAD - In Login - "Who are you?" should be replaced with "I am" | Jeba Raj | OK |  |  | New | 3 - Low | Functional | 2018-01-20 | 2018-01-25 |  | Fixed
3 | iPAD - Upon Wait "Reason to Postpone" is not mandatory; Replace all "Postpond" to "Postpone" | Jeba Raj | OK |  |  | New | 3 - Low | Functional | 2018-01-20 |  |  | Web Changes are pending
4 | iPAD - While creating General appointments are displayed as Urgent, and General tab does not display general appointments either. | Jeba Raj | Not resolved. | Not resolved |  | New | 1 - High | Functional | 2018-01-20 | 2018-01-25 |  | Fixed
5 | iPAD - Carry forward tab should display only past day's appointments, If current date is 20-Jan-2018, then only less that 20-Jan-18 appointments should display, but currently its displaying current date appointment also. | Jeba Raj | Not resolved. | Not resolved |  | New | 1 - High | Functional | 2018-01-20 |  |  | Web Changes are pending
6 | iPAD - if more than one appointments are sent from Web, the Chairman icon on desktop is still displaying as 1, the actual count should be displayed and the indication should display in iPAD application. For example, if there is a un-read general appointment, while opening the APP, currently opens in Urgent tab, but there should be an indication on general tab that, there is General appointments that needs to be attended. | Jeba Raj | OK | Not resolved | New | New | 1 - High | Functional | 2018-01-20 |  |  | New Features
7 | iPAD - On CarryForward tab, on click of Ok the record should disappear, but should display on WEB; "CarryForward" should be "Carry forward" | Jeba Raj | ?? |  |  | New | 2 - Medium | Functional | 2018-01-20 |  |  | Web Changes are pending
8 | iPAD - Settings should be moved from iPAD to WEB application | Jeba Raj | OK |  |  | New | 2 - Medium | Functional | 2018-01-20 | 2018-01-25 |  | Fixed
9 | iPAD - Once all tabs are visited and go back to desktop, the chairman icon still displays 1 un-responded appointment. It should display actual count of appointment notifications received. | Jeba Raj | OK | Not resolved | New | New | 1 - High | Functional | 2018-01-20 |  |  | New Features
10 | iPAD - If urgent type notification is received then, on clicking the notification message, the VMS should directly open Urgent tab, the same for General type appointment notification message click should open General tab. | B Suresh Kumar | Not resolved. | Not resolved | New | New | 2 - Medium | Functional | 2018-01-20 |  |  | New Features
11 | iPAD - VMS closes abruptly, without any action, (it happened 3-4 times during DEMO to Jeba sir) | Jeba Raj | OK |  |  | New | 2 - Medium | Functional | 2018-01-20 | 2018-01-25 |  | Fixed
12 | iPAD - Login as Deputy Chairmain -> General Tab - Rename "Click" to "Respond"; iPAD - Click the "Click" link -> On selecting any of the options -> should go back to previous page,. User should not be allowed to click on respond menu. Cancel menu is needed. | Jeba Raj | Not resolved. Still user needs to click on response after selecting option | OK |  | New | 2 - Medium | Technical | 2018-01-20 | 2018-01-25 |  | Fixed
13 | iPAD - Every tab loading takes more time. Needs to optimize the loading time | Jeba Raj | It is comparatively better. To be observed | It is comparatively better. To be observed | It is comparatively better. To be observed | New | 2 - Medium | Functional | 2018-01-20 |  |  | New Features
14 | iPAD - Login as Deputy Chairmain -> General Tab - Respond to 3rd record, first record gets affected and disappears. | Jeba Raj | OK |  |  | New | 1 - High | Functional | 2018-01-20 | 2018-01-25 |  | Fixed
15 | iPAD - Login as Chairman or Deputy Chairmain -> Differentiate the Tab contents with Tab label by a color | Jeba Raj | Not done. Blue color should be given for the selected tab. | OK |  | New | 4 - Cosmetic | Functional | 2018-01-20 |  |  | Need color confirmation
17 | WEB - New menu called Settings to hide and show the tabs in iPAD, based on that the category should be displayed in the drop down. | Jeba Raj | Not done. | Not resolved | Bug | New | 2 - Medium | Functional | 2018-01-20
18 | WEB - Auto Refresh in WEB is inconsistent | Jeba Raj | OK |  |  | New | 2 - Medium | Functional | 2018-01-20
19 | WEB - Paging issue, second page navigation is not responding, Paging does not work | Jeba Raj | Not Done | OK |  | New | 1 - High | Technical | 2018-01-20
20 | WEB - Notification from WEB to tab is very slow | Jeba Raj | OK. To be observed | OK. To be observed | Ok. To be observed | New | 2 - Medium | Functional | 2018-01-20
21 | WEB - Date should be displayed clearly and time should refresh based on system time | B Suresh Kumar | Not done | Not resolved |  | New | 2 - Medium | Functional | 2018-01-20
22 | WEB - When any tab (Urgent/General), in the message priority respective values should not appear. Also both General and Urgent cannot be disabled together. Currently, even if let us say urgent tab is disabled, system is permitting the user to request for appointment with urgent priority but messages are not saved. | Jeba Raj | New Bug | Not resolved | New | Bug | 1- High
23 | IPAD - Alignment of the "Created on", "Visitor Name" etc to be corrected | Jeba Raj | New Bug | OK |  | Bug | 1- High
24 | IPAD - Created date is appearing but time is not appearing as displayed in the web module | Jeba Raj | New Bug | OK |  | Bug | 1- High
25 | IPAD - "OK" ,"Wait", "Cancel" should be displayed in bold | Jeba Raj | New | OK |  | New | 1- High
26 | IPAD - Carry forward items are not in order | Jeba Raj | New Bug | OK |  | Bug | 1- High
27 | IPAD - Sanmar Logo to be displayed instead of some picture which is not relevant to Sanmar in the opening screen | Jeba Raj | New | OK |  | New | 1- High
28 | IPAD - Messages related to both Chairman or ViceChairman is getting displayed in the IPAD even if no one has logged in. Explanation given by KKMSoft is that it is getting displayed based on device token registered even if they haven't logged in. This is OK but needs to be extensively tested with two IPAD's to ensure that no irrelevant message is reaching them. | Jeba Raj |  | Needs further testing | Needs further testing | New | 1-High
29 | WEB - Password should be encrypted. Minimum Eight Character with one uppercase, one lowercase and one numeric atleast. This is a basic standard. Currently it is permitting any password to be set and also the password is stored as clear text. | Jeba Raj |  | Bug | Not a Bug | Bug | 1-High
30 | IPAD - In the Chairman screen wait option, option "response" and "cancel" is given for his response. It should be "OK", "Wait" and "Reject" | Jeba Raj |  | Bug |  | Bug | 1-High
31 | WEB - System is automatically refreshing and scrolling to the last line of the page when the receptionist is trying to enter data. | Jeba Raj |  | New bug | Not a Bug | Bug | 1- High
32 | IPAD - When we move between the tabs, previous tab data is still showing under the new tab while the new tab data is getting loaded. | Jeba Raj |  |  | Bug | Hygiene | 2-Med
33 | WEB - When the meeting is postponed in chairman screen, rescheduled meeting time is not displayed in the receiptionist screen. | Jeba Raj |  |  | New | Hygiene | 1-High
34 | IPAD - SANMAR VMS is opened, I am in Urgent tab, when I cancel a notification, the application minimized and desktop is displayed | B Suresh Kumar
35 | IPAD - SANMAR VMS is opened, I am in general tab, I receive a notification, I say ok, the tab is not refreshed when I receive a general appointment, but when I switch to urgent and come back to general then the appointment is displayed | B Suresh Kumar
36 | IPAD - Carry Forward is displaying Current date records only (both Chairman & Dty Chairman) Scenario : Hide Urgent or General tab for both Chairman & Dty Chairman - Hidden tab's Data is displayed in Carry Forward | B Suresh Kumar | [13 empty] | New
37 | IPAD - For Deputy Chairman, Urgent tab was hidden, but in iPAD it is visible, but general appointment notification is received. | B Suresh Kumar | [13 empty] | Open
38 | IPAD - When resaon to pospone text is typed and click ok the iPAD logs out and minimizes | B Suresh Kumar | [13 empty] | Resolved
39 | IPAD - Even if a particular tab is hidden for Chairman /Deputy Chairman, inconsitently (some it is , some times it is not) it is displayed in their screen | Jeba Raj |  |  | Bug | [10 empty] | Closed
40 | [15 empty] | Not an Issue
41 | [15 empty] | Not reprocible
Software Limitation
Verified